## Table 1
AriStay App — Developer Requirements Document (MVP / Must-Have Features) | Server Logics | Webapp | Mobile iOS | Progress | Auto Notes | LastUpdated
1. User Roles & Permissions
• Admin/Manager
o Full control: create, assign, update tasks & schedules. | 100% | 100% |  | Completed | Recurring schedules implemented: templates, auto task generation, cron-ready. | 2025-09-06 06:39:53Z
o Access to all reports, chat, and incident handling. | 90% | 90% |  | Partially Implemented | Infrastructure ready (notifications, devices, AJAX); UI/WebSocket chat pending. | 2025-09-06 06:39:53Z
o Approve/review proof-of-work and inventory logs. | 90% | 90% |  | Partially Implemented | Inventory management implemented: par levels, transactions, photos, alerts, staff UI. | 2025-09-06 06:39:53Z
• Cleaning Staff
o Access only assigned cleaning & To-Do tasks. | 100%
o Complete checklists, upload photos, report shortages/damages. | 100% |  |  | Completed | Comprehensive checklist system implemented: templates, responses, photos, progress, portal UI. | 2025-09-06 06:39:53Z
o Log lost & found items. | 100% |  |  | Completed | Lost & Found implemented: full lifecycle, photos, associations, search & filters. | 2025-09-06 06:39:53Z
• Maintenance Staff
o Access assigned maintenance + inventory tasks. | 100% |  |  | Completed | Inventory management implemented: par levels, transactions, photos, alerts, staff UI. | 2025-09-06 06:39:53Z
o Restock and log supply usage. | 90%
o Submit status updates, photos, and notes. | 100%
• Laundry Staff
o Access laundry-specific tasks (pick-up, wash/dry, drop-off, restock). | 90%
o Log shortages or damaged linens. | 90%
• Lawn/Pool Vendors
o Access assigned lawn/pool care tasks only. | 100%
o Submit proof-of-work (photos, GPS check-in/out). | 100% |  |  | Partially Implemented | Mobile-ready UI; pending coordinate capture/validation. | 2025-09-06 06:39:53Z
• Property Owner/Viewer (optional future) | 100%
o Read-only view of reports and property readiness status. | 90% |  |  | Not Implemented | Basic metrics exist; advanced reporting/SLA dashboards not built yet. | 2025-09-06 06:39:53Z
2. Core Modules & Features
A. Cleaning Schedule Management |  |  |  | Completed | Recurring schedules implemented: templates, auto task generation, cron-ready. | 2025-09-06 06:39:53Z
• Import daily cleaning schedules (check-in/check-out based). | 100% |  |  | Completed | Enhanced Excel import with conflict detection & resolution UI; templates and logs. | 2025-09-06 06:39:53Z
• Calendar view of all cleaning tasks. |  |  |  | Completed | Multiple dashboards implemented with analytics, refresh, and responsive UI. | 2025-09-06 06:39:53Z
• Daily To-Do list for cleaners (push notification + in-app). | 100%
• Room-by-room checklists with blocking steps. |  |  |  | Completed | Comprehensive checklist system implemented: templates, responses, photos, progress, portal UI. | 2025-09-06 06:39:53Z
• Damage/Loss report field inside checklist. |  |  |  | Completed | Comprehensive checklist system implemented: templates, responses, photos, progress, portal UI. | 2025-09-06 06:39:53Z
• Lost & Found log with photo uploads. |  |  |  | Completed | Lost & Found implemented: full lifecycle, photos, associations, search & filters. | 2025-09-06 06:39:53Z
• Proof of work: before/after photos, GPS + timestamp. |  |  |  | Partially Implemented | Mobile-ready UI; pending coordinate capture/validation. | 2025-09-06 06:39:53Z
B. To-Do Management
• Admin can create additional daily tasks.
• Auto-updates staff To-Do list with notifications.
• Task statuses: Pending → In Progress → Completed.
C. Communication & Incident Handling
• In-app chat between Admin ↔ Cleaning staff, Admin ↔ Maintenance staff. |  |  |  | Partially Implemented | Infrastructure ready (notifications, devices, AJAX); UI/WebSocket chat pending. | 2025-09-06 06:39:53Z
• Supports photos/videos for issue reporting. |  |  |  | Not Implemented | Basic metrics exist; advanced reporting/SLA dashboards not built yet. | 2025-09-06 06:39:53Z
• Urgent alerts for critical issues.
• Chat threads linked to property/task. |  |  |  | Partially Implemented | Infrastructure ready (notifications, devices, AJAX); UI/WebSocket chat pending. | 2025-09-06 06:39:53Z
D. Image Upload & AI Quality Assurance |  |  |  | Partially Implemented | Upload pipeline complete; pending AI/computer vision quality checks. | 2025-09-06 06:39:53Z
• Before/after photos required for cleaning.
• AI detects missed cleaning details (stains, residue, clutter). |  |  |  | Partially Implemented | Upload pipeline complete; pending AI/computer vision quality checks. | 2025-09-06 06:39:53Z
• Generates automated quality alerts for Admin.
• Reports stored and linked to property & date. |  |  |  | Not Implemented | Basic metrics exist; advanced reporting/SLA dashboards not built yet. | 2025-09-06 06:39:53Z
E. Maintenance Schedule Management |  |  |  | Completed | Recurring schedules implemented: templates, auto task generation, cron-ready. | 2025-09-06 06:39:53Z
• Admin creates/updates tasks (color-coded).
• Tasks assigned to staff or open to claim.
• Unified calendar view (with cleaning schedules). |  |  |  | Completed | Multiple dashboards implemented with analytics, refresh, and responsive UI. | 2025-09-06 06:39:53Z
• Notifications/reminders for due tasks.
• Statuses: Pending → In Progress → Completed.
• Weekly/monthly reports on property issues. |  |  |  | Not Implemented | Basic metrics exist; advanced reporting/SLA dashboards not built yet. | 2025-09-06 06:39:53Z
F. Supplies Inventory Management (NEW) |  |  |  | Completed | Inventory management implemented: par levels, transactions, photos, alerts, staff UI. | 2025-09-06 06:39:53Z
• Property Inventory Profiles |  |  |  | Completed | Inventory management implemented: par levels, transactions, photos, alerts, staff UI. | 2025-09-06 06:39:53Z
o Track consumables: toilet paper, soap, trash bags, light bulbs, batteries, AC filters, pool chemicals, etc.
o Define par levels per property.
• Stock-in / Stock-out Logging |  |  |  | Completed | Inventory management implemented: par levels, transactions, photos, alerts, staff UI. | 2025-09-06 06:39:53Z
o Maintenance logs items replenished/used.
o Cleaning staff can flag shortages → auto-creates inventory task for maintenance. |  |  |  | Completed | Inventory management implemented: par levels, transactions, photos, alerts, staff UI. | 2025-09-06 06:39:53Z
• Alerts
o Low-stock notifications to Admin when levels drop below par. |  |  |  | Completed | Inventory management implemented: par levels, transactions, photos, alerts, staff UI. | 2025-09-06 06:39:53Z
o Urgent shortages flagged inside system.
• Proof & Audit
o Photo uploads for restocked items.
o Historical log of usage by date, property, and staff.
• Reporting |  |  |  | Not Implemented | Basic metrics exist; advanced reporting/SLA dashboards not built yet. | 2025-09-06 06:39:53Z
o Weekly/monthly supply usage reports. |  |  |  | Not Implemented | Basic metrics exist; advanced reporting/SLA dashboards not built yet. | 2025-09-06 06:39:53Z
o Exportable CSV/PDF for budgeting and owner reporting. |  |  |  | Not Implemented | Basic metrics exist; advanced reporting/SLA dashboards not built yet. | 2025-09-06 06:39:53Z
G. Laundry Management
• Task types: pick-up, wash/dry, drop-off, restock.
• Checklist: linens counted in/out, condition logged. |  |  |  | Completed | Comprehensive checklist system implemented: templates, responses, photos, progress, portal UI. | 2025-09-06 06:39:53Z
• Staff can mark shortages or damaged linens.
• Proof of work: photo upload for delivery/restock.
• Integrated with Inventory module for linen counts. |  |  |  | Completed | Inventory management implemented: par levels, transactions, photos, alerts, staff UI. | 2025-09-06 06:39:53Z
H. Lawn & Pool Care Management
• Recurring/one-time schedules for mowing, edging, fertilization, pool cleaning, chemical checks. |  |  |  | Completed | Recurring schedules implemented: templates, auto task generation, cron-ready. | 2025-09-06 06:39:53Z
• Property-specific profiles (yard size, pool type, access notes).
• Proof of work: photos, GPS check-in/out. |  |  |  | Partially Implemented | Mobile-ready UI; pending coordinate capture/validation. | 2025-09-06 06:39:53Z
• Alerts for overdue tasks or missed check-ins.
• Roles/permissions restricted by team.
3. Reporting & Oversight |  |  |  | Not Implemented | Basic metrics exist; advanced reporting/SLA dashboards not built yet. | 2025-09-06 06:39:53Z
• Cleaning Reports: task completion, SLA compliance. |  |  |  | Not Implemented | Basic metrics exist; advanced reporting/SLA dashboards not built yet. | 2025-09-06 06:39:53Z
• Maintenance Reports: weekly/monthly logs of issues & resolutions. |  |  |  | Not Implemented | Basic metrics exist; advanced reporting/SLA dashboards not built yet. | 2025-09-06 06:39:53Z
• Inventory Reports: usage, shortages, and restocking costs. |  |  |  | Completed | Inventory management implemented: par levels, transactions, photos, alerts, staff UI. | 2025-09-06 06:39:53Z
• Laundry Reports: linen counts, shortages, damages. |  |  |  | Not Implemented | Basic metrics exist; advanced reporting/SLA dashboards not built yet. | 2025-09-06 06:39:53Z
• Lawn/Pool Reports: completion rates, overdue alerts. |  |  |  | Not Implemented | Basic metrics exist; advanced reporting/SLA dashboards not built yet. | 2025-09-06 06:39:53Z
• Exports: CSV/PDF for admin and property owner reporting. |  |  |  | Not Implemented | Basic metrics exist; advanced reporting/SLA dashboards not built yet. | 2025-09-06 06:39:53Z
4. Notifications & Alerts
• Daily To-Do reminders for staff.
• Task reminders (24h before, 2h before start).
• Alerts for overdue/missed check-ins.
• Low-stock and shortage notifications. |  |  |  | Completed | Inventory management implemented: par levels, transactions, photos, alerts, staff UI. | 2025-09-06 06:39:53Z
• AI QA alerts for failed photo inspections. |  |  |  | Partially Implemented | Upload pipeline complete; pending AI/computer vision quality checks. | 2025-09-06 06:39:53Z
• Urgent issue alerts from staff.
5. Acceptance Criteria (MVP “Definition of Done”)
• Admin uploads schedule → auto-generates cleaning/maintenance/lawn/pool tasks. |  |  |  | Completed | Recurring schedules implemented: templates, auto task generation, cron-ready. | 2025-09-06 06:39:53Z
• Staff get push notifications → complete checklists & upload proof. |  |  |  | Completed | Comprehensive checklist system implemented: templates, responses, photos, progress, portal UI. | 2025-09-06 06:39:53Z
• Tasks cannot be marked complete without required checklists/photos. |  |  |  | Completed | Comprehensive checklist system implemented: templates, responses, photos, progress, portal UI. | 2025-09-06 06:39:53Z
• AI auto-checks cleaning photos → alerts admin if issues detected. |  |  |  | Partially Implemented | Upload pipeline complete; pending AI/computer vision quality checks. | 2025-09-06 06:39:53Z
• Damages/lost items reported with photo & logged.
• Cleaning shortages auto-generate inventory tasks → maintenance team replenishes & logs. |  |  |  | Completed | Inventory management implemented: par levels, transactions, photos, alerts, staff UI. | 2025-09-06 06:39:53Z
• Weekly/monthly reports auto-generate & export. |  |  |  | Not Implemented | Basic metrics exist; advanced reporting/SLA dashboards not built yet. | 2025-09-06 06:39:53Z
• Unified calendar shows all tasks across teams. |  |  |  | Completed | Multiple dashboards implemented with analytics, refresh, and responsive UI. | 2025-09-06 06:39:53Z
• In-app chat supports staff-admin coordination with media sharing. |  |  |  | Partially Implemented | Infrastructure ready (notifications, devices, AJAX); UI/WebSocket chat pending. | 2025-09-06 06:39:53Z
6. Technical Notes
• Mobile-first (Android/iOS with offline mode).
• Shared task engine & calendar across all modules. |  |  |  | Completed | Multiple dashboards implemented with analytics, refresh, and responsive UI. | 2025-09-06 06:39:53Z
• Photo compression + GPS/timestamp metadata. |  |  |  | Partially Implemented | Mobile-ready UI; pending coordinate capture/validation. | 2025-09-06 06:39:53Z
• Push notifications for all role types.
• CSV/PDF reporting exports. |  |  |  | Not Implemented | Basic metrics exist; advanced reporting/SLA dashboards not built yet. | 2025-09-06 06:39:53Z
• AI module for photo QA |  |  |  | Partially Implemented | Upload pipeline complete; pending AI/computer vision quality checks. | 2025-09-06 06:39:53Z

## Status Update
Feature | Status | Notes | LastUpdated
Checklist System | Completed | Comprehensive checklist system implemented: templates, responses, photos, progress, portal UI. | 2025-09-06 06:39:53Z
Inventory Management | Completed | Inventory management implemented: par levels, transactions, photos, alerts, staff UI. | 2025-09-06 06:39:53Z
Lost & Found | Completed | Lost & Found implemented: full lifecycle, photos, associations, search & filters. | 2025-09-06 06:39:53Z
Recurring Schedule System | Completed | Recurring schedules implemented: templates, auto task generation, cron-ready. | 2025-09-06 06:39:53Z
Excel Import/Export | Completed | Enhanced Excel import with conflict detection & resolution UI; templates and logs. | 2025-09-06 06:39:53Z
Calendar/Dashboards | Completed | Multiple dashboards implemented with analytics, refresh, and responsive UI. | 2025-09-06 06:39:53Z
Chat System | Partially Implemented | Infrastructure ready (notifications, devices, AJAX); UI/WebSocket chat pending. | 2025-09-06 06:39:53Z
AI Photo QA | Partially Implemented | Upload pipeline complete; pending AI/computer vision quality checks. | 2025-09-06 06:39:53Z
GPS Integration | Partially Implemented | Mobile-ready UI; pending coordinate capture/validation. | 2025-09-06 06:39:53Z
Advanced Analytics/Reporting | Not Implemented | Basic metrics exist; advanced reporting/SLA dashboards not built yet. | 2025-09-06 06:39:53Z
Third-party Integrations | Not Implemented | No direct Airbnb/VRBO/PMS integrations yet; Excel-based flow only. | 2025-09-06 06:39:53Z